## Tabelle1
Studenliste von Sebastian Ederer
Projekt Redpitaya Oszilloskop
Datum | Zeit (0,5h genau) | Zwischensumme (fortlaufend aufsummiert) | Tätigkeit | Unterschrift
2021-03-21 | 0.5 | 0.5 | Fixed git-merging issues
2021-04-05 | 6 | 6.5 | Organizational stuff; Research on jquery-ui
2021-04-12 | 5.5 | 12 | Research and experimenting with jquery-ui
2021-04-17 | 8 | 20 | Implemented Zooming-Feature with jquery-ui; vue-routing
2021-04-22 | 4 | 24 | Meeting + css fix
2021-04-26 | 6 | 30 | Debugged webui on actual mobile device
2021-05-01 | 8 | 38 | Added touch-support for jqueryui, fixed routing & merge issues
2021-05-02 | 9 | 47 | Fixed vue routing; started to implement data receiving
2021-05-03 | 6 | 53 | Implemented uPlot as apexcharts cannot handle big data
2021-05-20 | 3 | 56 | Meeting + bug fixing
2021-06-03 | 8 | 64 | Worked on uPlot; Meeting
2021-06-04 | 6 | 70 | Bug fixing; Research + working on uPlot and data visualization
2021-06-07 | 7 | 77 | Implemented zooming for uPlot.
2021-06-10 | 1 | 78 | Meeting; Fixed bug for uplot grip ranger
2021-07-19 | 7 | 85 | Started implementing data annotations
2021-07-29 | 1.5 | 86.5 | Meeting + synced data annotation chart with range gripper
2021-08-04 | 2.5 | 89 | Meeting + implemented conditional rendering for annotations
2021-08-05 | 6 | 95 | Improved data annotations. Started to improve chart navigation
2021-08-20 | 7 | 102 | Research on canvas and experimenting mit UI/UX design.
2021-08-25 | 1 | 103 | Research on UI/UX for chart navigation
2021-09-03 | 4 | 107 | Further implemented chart navigation
2021-09-04 | 3 | 110 | Further implemented chart navigation
2021-09-06 | 2 | 112 | Meeting
2021-09-08 | 6 | 118 | Chart navigation (mobile support)
2021-09-09 | 1 | 119 | Meeting
2021-09-13 | 1 | 120 | Videoaufnahme, bug fixing
2021-09-17 | 4 | 124 | Poster
2021-09-18 | 6 | 130 | Implemented DecodedData, Fixes
2021-09-18 | 2 | 132 | Präsentation
2021-09-19 | 4 | 136 | Dokumentation
2021-09-20 | 3 | 139 | Videoschnitt
2021-09-21 | 2 | 141 | Videoschnitt
2021-09-22 | 4 | 145 | Audiomixing für Video, Videoschnitt